## Slide 1
THE MEDCHRONS PILOT — WORKING PLAN
The execution detail behind the pitch
Companion to the onboarding tracker (.xlsx) · Lakefront Injury Group (sample).
Prepared by Alex Donnelly · Customer Onboarding Specialist (sample)
Independent work sample from EvenUp's public materials. Not affiliated with or endorsed by EvenUp. Fictional firm; figures illustrative.

## Slide 2
THE 90-DAY ARC
Five phases, each with an exit
You don't move on until the exit condition is met. Owners and status live in the tracker.
1
Discover
Days 1–15
2
Configure
Days 16–30
3
Pilot
Days 31–60
4
Measure
Days 61–75
5
Expand
Days 76–90

## Slide 3
PILOT SCOPE
A small, deliberately chosen cohort
1
The cohort
2 attorneys, 4 paralegals, 1 records liaison, 1 champion — ~15–25 matters.
2
Include
Standard MVC & premises matters with records collected.
3
Exclude at first
Catastrophic or highly fragmented files — unless complexity is the test.
4
Cadence
Weekly huddle, shared issue log, weekly completed-matter review.

## Slide 4
THE DISCIPLINE THAT MAKES IT REAL
The closed-loop review
Seven questions on every completed MedChron — what turns training into operational learning.
1. Was it submitted at the right stage of the case?
2. Was the source packet ready — records, bills, providers, dates?
3. Did the chronology surface something genuinely useful?
4. Did the paralegal need to correct, supplement, or clarify?
5. Did the attorney use it in evaluation, demand, or strategy?
6. Were missing records or treatment gaps identified?
7. Would the team use it again on the next eligible matter?

## Slide 5
ON-SITE · GO-LIVE WEEK
The intensive training week
Champions first; every role trains on its own real cases.
WHO
FOCUS
Mon
Leadership & champions
Confirm vision & metrics; finalize configuration on live cases
Tue
Records & intake
Submission readiness — records, bills, provider list; naming & handoffs
Wed
Paralegals & medical
Build & review the MedChron; review-against-source on every chronology
Thu
Attorneys
Using the chronology in evaluation, valuation & demand prep
Fri
Whole cohort
Go-live, office hours, success-plan check, closed-loop review demo

## Slide 6
CHANGE MANAGEMENT
What good looks like — by role
Full role detail lives in the tracker; here's the outcome for each.
Attorney
Works from a verified chronology; trusts it because they know how to check it.
Paralegal & medical
Shifts from extraction to verification, gap-spotting, case-story development.
Case manager
Acts on surfaced gaps early — records requests, treatment follow-up.
Records & admin
Predictable file readiness; clean handoffs; less downstream rework.
Sponsor / ops lead
Watches adoption health, clears blockers, reinforces the behavior.

## Slide 7
MEASUREMENT
What we'd measure together
Operational value — not downstream settlement lift, which is hard to isolate in 90 days.
Adoption
% of eligible matters using the workflow
Speed
Days: record-ready → attorney-ready
Efficiency
Paralegal time per chronology
Quality
Corrections / escalations per matter
Utility
% attorneys who say it accelerated review
Confidence & reuse
Confidence; repeat use as support tapers

## Slide 8
ACCOUNT HEALTH
Keeping it on track after go-live
SIGNAL
HEALTHY
AT-RISK → ACTION
Utilization
Most eligible matters use it
Falling → office hours, re-train, recheck config
Trust in output
Teams rely on reviewed drafts
Quiet distrust → coach review habit, show citations
Champion engagement
Active, responsive champion
Quiet/departed → re-establish a sponsor
Quality
Few material corrections
Rising → tighten readiness & review checklists

## Slide 9
The plan, tracked.
This deck is the working detail; the companion .xlsx runs it — owners, status, and exit criteria for every step.
Alex Donnelly · a.james.donnelly@gmail.com · ajdonnelly.github.io/evenup-onboarding
Independent work sample from EvenUp's public materials. Not affiliated with or endorsed by EvenUp. Fictional firm; figures illustrative.