## Overview
MedChrons Adoption Pilot — Command Center
Lakefront Injury Group (fictional) · a bounded 90-day MedChrons pilot
Adoption starts with the work already happening inside the firm, not the technology. This workbook runs one
high-value workflow — medical chronologies — as a controlled pilot: discover, configure, pilot, measure, expand.
Built on EvenUp's change-management model (Set the Vision / Empower the Firm / Make the Change Stick).
Tabs: Pilot Charter · 90-Day Plan · Matter Tracker · Readiness Checklist · Cohort Tracker · Issue Log · Baseline & Outcomes
Prepared by Alex Donnelly · Customer Onboarding Specialist (sample). Independent work sample from EvenUp's public
materials; not affiliated with or endorsed by EvenUp. Firm, names, and figures are illustrative.

## Pilot Charter
Item | Detail
Workflow | Medical chronologies (MedChrons): build, review, and act
Why this workflow | High-frequency, high-friction; touches records, treatment timeline, damages, attorney review, demand prep
Cohort | 1 office / 1 practice group: 2 attorneys, 4 paralegals, 1 case-manager & records liaison, 1 firm champion
Matter volume | ~15–25 eligible matters
Include | Standard MVC & premises matters with records collected and a defined treatment window
Exclude at first | Catastrophic injuries, highly fragmented records, heavy active treatment (unless complexity is the test)
Phases | Discover (Days 1–15) · Configure (16–30) · Pilot (31–60) · Measure (61–75) · Expand (76–90)
Cadence | Daily huddle first 2 weeks; then weekly pilot huddle; shared issue log; weekly completed-matter review
Core habit | Review AI output against the source before relying on it
Success (90 days) | A trusted, repeatable behavior with measurable operational value and a clear path to scale
Not claimed in 90 days | Downstream settlement lift — real at scale, hard to isolate quickly
Sponsor / champion | [Ops lead] · [Named champion]

## 90-Day Plan
Phase | Window | Activity | Owner | Status
1 · Discover & baseline | Days 1–15 | Leadership kickoff; align on success metrics | Specialist + Sponsor | Not started
|  | Role interviews (attorneys, paralegals, case managers, records) | Specialist | Not started
|  | Walk through 3–5 recent matters; map current chronology process | Specialist | Not started
|  | Choose cohort & eligibility; capture baseline cycle-time/effort | Specialist + Champion | Not started
EXIT: current-state map, pilot charter, baseline scorecard, risk register, eligibility criteria
2 · Design & configure | Days 16–30 | Design Lakefront's target workflow (readiness → review → act) | Specialist + Champion | Not started
|  | Configure EvenUp to CMS & SOPs; build role quick-reference guides | Specialist | Not started
EXIT: future-state map, RACI, review checklist, escalation matrix, pilot roster
3 · Run the pilot | Days 31–60 | On-site training week (champions first) | Specialist | Not started
|  | Go live on eligible matters; daily then weekly huddles | Cohort + Champion | Not started
|  | Closed-loop review on every completed MedChron; coach review-against-source | Specialist + Paralegals | Not started
EXIT: every role trained; first chronologies produced, QC'd, used by attorneys
4 · Measure & refine | Days 61–75 | Build pilot scorecard (operational + human); tune workflow rules | Specialist | Not started
|  | Draft evidence-based expansion recommendation | Specialist + Sponsor | Not started
EXIT: scorecard vs baseline; refined SOP; recommendation drafted
5 · Operationalize & expand | Days 76–90 | Expansion decision (continue/refine/expand/pause); v2 training | Specialist + Sponsor | Not started
|  | Champion network; 30/60/90 reinforcement; product feedback loop | Specialist | Not started
EXIT: outcomes report, v2 SOP & training, champion guide, reinforcement plan

## Matter Tracker
Matter ID | Case type | Attorney | Paralegal | Readiness date | Submitted | Delivered | Attorney review | Status | Notes
LIG-1042 | MVC | Reyes | Okafor |  |  |  |  | Ready
LIG-1057 | Premises | Reyes | Okafor |  |  |  |  | Submitted
LIG-1063 | MVC | Banks | Liu |  |  |  |  | In review
LIG-1071 | MVC | Banks | Liu |  |  |  |  | Attorney-ready
LIG-1088 | Premises | Reyes | Okafor |  |  |  |  | Not ready

## Readiness Checklist
Readiness item | Required? | Owner | Notes
Medical records collected for treatment window | Yes | Records
Bills present and matched to providers | Yes | Records
Provider list verified (names, facilities, dates) | Yes | Paralegal
Treatment date range confirmed; obvious gaps noted | Yes | Paralegal
Correct matter selected; files named to convention | Yes | Records
Known gaps flagged before submission | If applicable | Paralegal

## Cohort Tracker
Name | Role | Team / office | Trained | First use | Cases | Confidence (1–5) | Champion
Reyes | Attorney | North office
Banks | Attorney | North office
Okafor | Paralegal | North office |  |  |  |  | Yes
Liu | Paralegal | North office
Patel | Paralegal | North office
Greene | Paralegal | North office
Mora | Case manager / records | North office

## Issue Log
Issue | Type | Severity | Workflow stage | Owner | Status | Pattern / implication
Provider missing from chronology | Quality | Med | Submission readiness | Paralegal | Open | Tighten readiness check
Two visits merged into one entry | Quality | High | Review | Paralegal | Open | Add to review checklist
Attorney unsure what 'attorney-ready' means | Enablement | Low | Attorney review | Specialist | Resolved | Clarify in training

## Baseline & Outcomes
Metric | Baseline (pre-pilot) | Pilot result | Source
% of eligible matters using the workflow |  |  | Workflow log
Median days: record-readiness → attorney-ready chronology |  |  | Matter Tracker
Paralegal time per chronology |  |  | Time log / survey
Material corrections or escalations per matter |  |  | Issue Log
% attorneys who say it changed/accelerated review |  |  | Survey
Missing records / treatment gaps identified per matter |  |  | Matter Tracker
User confidence (1–5) |  |  | Cohort Tracker
Repeat use after support tapers |  |  | Workflow log